## risk
Working | Seriousness |  |  |  | Ethics | Seriousness
Likelihood |  | Low | Medium | High | Likelihood |  | Low | Medium | High
| Low |  | fail to work out solutions in one sprint(2) |  |  | Low |  | Need more ethical approval(2) | Data leakage(1)
| Medium | employee gets sick(4) |  |  |  | Medium
| High |  |  |  |  | High
| Mitigation |  |  |  |  | Mitigation
employee gets a cold(4) | Sicked employees work at home or cover their jobs by others |  |  |  | Need more ethical approvalt(2) | Apply for more ethical approval
fail to work out solutions in one sprint(2) | Work extra hours or cut down the time used for next sprint |  |  |  | fail to work out solutions in one sprint(2) | Trace back or destroy all disclosed data

## priority
Priority | Definition
1 | Vital – the final project will not work without this. Whatever the reason this was not planned from the outset, it must be done now. This may be as the result of something external to the product, such as changes in legislation.
2 | High - it would be very inconvenient to operate the product without this. Any work round can only be operated for a limited time. E.g. it might be acceptable to do this by hand during the month, but at year-end the volume of transactions will be too great to cope with.
3 | Medium - a work round can operate. E.g. the operator might have to return to the menu to select the next option rather than go straight there
4 | Low - nice-to-have, but can live without the change. This might include things like changing the order of fields on the screen, or having the grey fabric for the seat covers after all
5 | Cosmetic change – in practice these are very often implemented before higher priority ones, e.g. a minor screen change will be done while the code is open for some other reason. But if these changes are never done, they will not impact the benefits or usability from developing the product.